## Sheet1
Feature | Description | State | Duration
Products Component | Show list of products on the home page | Open | 2 | Time | 35 | Hours
Filter Component | Filter products based on their size and sort by price | Open | 2 | Rate | 30 | USD/Hour
Cart Component | Show selected item in the cart on the right sidebar | Open | 3 | Cost | 1050 | USD
Add Animation | Animated product list and adding to cart | Open | 2
Add Modal | Show Modal when user clicks on a product | Open | 2
Checkout Form | Show checkout form to get buyer data | Open | 2
Product Backend | Create a simple backend to send product to frontend | Open | 3
Add Redux | Create store, initial state, and reducer and redux devtools | Open | 2
Add Redux to Products | Move products state to redux | Open | 3
Add Redux to Filter | Move filter state to redux | Open | 3
Add Redux to Cart | Move cart state to redux | Open | 3
Create Order | Handle frontend and backend of creating an order | Open | 3
Add Admin Section | User react-router to create two routes for Home and Admin | Open | 2
Publish Heroku | Craae MongoDB atlas database and publish Heroku App | Open | 3